## Cover Sheet
Town: | Chatham
|  |  | MS4 Permit Task | Permit Year |  |  |  |  | # Yrs | % Complete | Estimated Hours |  | Work Distribution |  |  | Total Low Cost Estimate | [12 empty] | Total High Cost Estimate | [12 empty] | % Overall Cost
Community Statistics | [15 empty] | Annual Low Cost Estimates for Town | [5 empty] | Annual Low Cost Estimates for Consultant | [6 empty] | Annual High Cost Estimates for Town | [5 empty] | Annual High Cost Estimates for Consultant
General |  |  |  | 1 | 2 | 3 | 4 | 5 |  |  | Low | High | Town | Region | Consultant | YR1 | YR2 | YR3 | YR4 | YR5 | Town | YR1 | YR2 | YR3 | YR4 | YR5 | Consultant | 5-Yr Total | YR1 | YR2 | YR3 | YR4 | YR5 | Town | YR1 | YR2 | YR3 | YR4 | YR5 | Consultant | 5-Yr Total | Low | High
Population | 6125 |  | Notice of Intent (NOI) | x |  |  |  |  | 1 | 0% | 50 | 112 | 100% |  |  | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 11200 | 0 | 0 | 0 | 0 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 1.338% | 1.45%
# of households (=population / 2.4 if assumed) | 3025 |  | Stormwater Mgmt Plan (SWMP) | x |  |  |  |  | 1 | 0% | 128 | 204 | 100% |  |  | 12800 | 0 | 0 | 0 | 0 | 12800 | 0 | 0 | 0 | 0 | 0 | 0 | 12800 | 20400 | 0 | 0 | 0 | 0 | 20400 | 0 | 0 | 0 | 0 | 0 | 0 | 20400 | 3.425% | 2.642%
Population in regulated area | 6125 |  | MCM 1 - Public Education | x | x | x | x | x | 5 | 0% | 112 | 730 | 100% |  |  | 2240 | 2240 | 2240 | 2240 | 2240 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 14760 | 14760 | 14760 | 14760 | 14760 | 73800 | 0 | 0 | 0 | 0 | 0 | 0 | 73800 | 2.997% | 9.557%
Consultant Rate / hour | 100 |  | MCM 2 - Public Participation | x | x | x | x | x | 5 | 0% | 80 | 150 | 100% |  |  | 1800 | 1800 | 1800 | 1800 | 1800 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 3400 | 3400 | 3400 | 3400 | 3400 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 2.408% | 2.201%
|  |  | MCM 3 - IDDE | [7 empty] | 444.2 | 1193.36 | [8 empty] | 46919.8463 | [5 empty] | 0 | 46919.8463 | [5 empty] | 125128.9114 | [5 empty] | 0 | 125128.9114 | 12.55% | 16.2%
MCM3 - Illicit Discharge Detection and Elimination |  |  | Written IDDE Plan / Procedures | x |  |  |  |  | 1 | 0% | 16 | 48 | 100% |  |  | 1600 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 4800 | 0 | 0 | 0 | 0 | 4800 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 0.4281% | 0.6216%
Number of outfalls | 12 |  | System Mapping / Catchment Delineation | x | x |  |  |  | 2 | 0% | 134.8 | 656.56 | 100% |  |  | 6740 | 6740 | 0 | 0 | 0 | 13480 | 0 | 0 | 0 | 0 | 0 | 0 | 13480 | 33601 | 33601 | 0 | 0 | 0 | 67202 | 0 | 0 | 0 | 0 | 0 | 0 | 67202 | 3.607% | 8.702%
Number of catch basins (10 per outfall if assumed) | 773 |  | Catchment Assessment / Ranking | x | x | x |  |  | 3 | 0% | 24 | 160 | 100% |  |  | 800 | 800 | 800 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 5333.3333 | 5333.3333 | 5333.3333 | 0 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 0.6421% | 2.072%
Key junction manholes (20% of CBs) / (3 per outfall) | 154.6 | 36 | Dry Weather Screening | x | x | x |  |  | 3 | 0% | 132 | 212 | 100% |  |  | 4579.0392 | 4579.0392 | 4579.0392 | 0 | 0 | 13737.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 13737.1176 | 7245.7059 | 7245.7059 | 7245.7059 | 0 | 0 | 21737.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 21737.1176 | 3.675% | 2.815%
Assumed % outfalls flowing under dry conditions | 10% |  | Wet Weather Screening |  |  | x | x | x | 3 | 0% | 2.4 | 7.2 | 100% |  |  | 0 | 0 | 108.3823 | 108.3823 | 108.3823 | 325.147 | 0 | 0 | 0 | 0 | 0 | 0 | 325.147 | 0 | 0 | 325.147 | 325.147 | 325.147 | 975.441 | 0 | 0 | 0 | 0 | 0 | 0 | 975.441 | 0.08699% | 0.1263%
Catchments with SVFs for wet sampling (low estimate - 25%) | 3 |  | Catchment Investigations |  | x | x | x | x | 4 | 0% | 35 | 9.6 | 100% |  |  | 0 | 1219.3954 | 1219.3954 | 1219.3954 | 1219.3954 | 4877.5817 | 0 | 0 | 0 | 0 | 0 | 0 | 4877.5817 | 0 | 478.5882 | 478.5882 | 478.5882 | 478.5882 | 1914.3528 | 0 | 0 | 0 | 0 | 0 | 0 | 1914.3528 | 1.305% | 0.2479%
Catchments with SVFs for wet sampling (high estimate - 75%) | 9 |  | Training | x | x | x | x | x | 5 | 0% | 100 | 100 | 100% |  |  | 2100 | 2100 | 2100 | 2100 | 2100 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 2500 | 2500 | 2500 | 2500 | 2500 | 12500 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 2.809% | 1.619%
Maximum # of illicit discharge incidents (min/max) | 1 | 1 | MCM 4 - Construction Site Control | [7 empty] | 32 | 96 | [8 empty] | 4200 | [5 empty] | 0 | 4200 | [5 empty] | 21600 | [5 empty] | 0 | 21600 | 1.124% | 2.797%
|  |  | Update of construction bylaw/ordinance | x |  |  |  |  | 1 | 0% | 32 | 40 | 100% |  |  | 4200 | 0 | 0 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 6000 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 1.124% | 0.777%
MCM4 - Construction Site Control |  |  | Construction review / site inspection procedures | x |  |  |  |  | 1 | 0% | 0 | 56 | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15600 | 0 | 0 | 0 | 0 | 15600 | 0 | 0 | 0 | 0 | 0 | 0 | 15600 | 0% | 2.02%
Annual construction projects w/site inspection paid by town (min/max) | 1 | 1 | MCM 5 - Post Construction Site Control | [7 empty] | 622 | 764 | [8 empty] | 65200 | [5 empty] | 0 | 65200 | [5 empty] | 82400 | [5 empty] | 0 | 82400 | 17.44% | 10.67%
|  |  | Update post construction regulations |  | x |  |  |  | 1 | 0% | 40 | 80 | 100% |  |  | 0 | 6000 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 12000 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 1.605% | 1.554%
MCM5 - Post Construction Site Control |  |  | Report on existing street / parking regulations |  |  |  | x |  | 1 | 0% | 62 | 116 | 100% |  |  | 0 | 0 | 0 | 7200 | 0 | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | 13600 | 0 | 13600 | 0 | 0 | 0 | 0 | 0 | 0 | 13600 | 1.926% | 1.761%
Number of municipal facilities for BMP evaluation | 65 |  | Inventory municipal properties |  |  |  | x |  | 1 | 0% | 520 | 568 | 100% |  |  | 0 | 0 | 0 | 52000 | 0 | 52000 | 0 | 0 | 0 | 0 | 0 | 0 | 52000 | 0 | 0 | 0 | 56800 | 0 | 56800 | 0 | 0 | 0 | 0 | 0 | 0 | 56800 | 13.91% | 7.355%
|  |  | MCM 6 - Good Housekeeping | [7 empty] | 581 | 782 | [8 empty] | 138100 | [5 empty] | 0 | 138100 | [5 empty] | 215700 | [5 empty] | 0 | 215700 | 36.95% | 27.93%
MCM6 - Good Housekeeping |  |  | Develop Operation / Maintenance Procedures |  | x |  |  |  | 1 | 0% | 344 | 388 | 100% |  |  | 0 | 34400 | 0 | 0 | 0 | 34400 | 0 | 0 | 0 | 0 | 0 | 0 | 34400 | 0 | 38800 | 0 | 0 | 0 | 38800 | 0 | 0 | 0 | 0 | 0 | 0 | 38800 | 9.204% | 5.024%
Number of community owned stormwater BMPs | 3 |  | BMP Inspection / Maintenance |  | x |  |  |  | 1 | 0% | 57 | 84 | 100% |  |  | 0 | 5700 | 0 | 0 | 0 | 5700 | 0 | 0 | 0 | 0 | 0 | 0 | 5700 | 0 | 8400 | 0 | 0 | 0 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 8400 | 1.525% | 1.088%
Number of facilities requiring SWPPPs (min/max) | 3 | 3 | SWPPP Written Plan Preparation |  | x |  |  |  | 1 | 0% | 0 | 0 | 100% |  |  | 0 | 15000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 4.013% | 1.942%
Town owned trucks for catch basin cleaning? (Yes / No) | Yes |  | SWPPP Implementation |  | x | x | x | x | 4 | 0% | 120 | 240 | 100% |  |  | 0 | 6750 | 6750 | 6750 | 6750 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 0 | 11625 | 11625 | 11625 | 11625 | 46500 | 0 | 0 | 0 | 0 | 0 | 0 | 46500 | 7.224% | 6.022%
Assumed % of structures requiring cleaning (>50% full) | 20% |  | Catch Basin Cleaning | x | x | x | x | x | 5 | 0% | 0 | 0 | 100% |  |  | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 6.689% | 6.475%
Number of structures requiring cleaning per year | 154.6 |  | Street Sweeping | x | x | x | x | x | 5 | 0% | 0 | 0 | 100% |  |  | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 6.689% | 6.475%
Town owned trucks for street sweeping? (Yes / No) | Yes |  | Training | x | x | x | x | x | 5 | 0% | 60 | 70 | 100% |  |  | 1200 | 1200 | 1200 | 1200 | 1200 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 1400 | 1400 | 1400 | 1400 | 1400 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 1.605% | 0.9065%
Miles of town owned (regulated) roadway | 67 |  | Annual Report | x | x | x | x | x | 5 | 0% | 253 | 516 | 100% |  |  | 5060 | 5060 | 5060 | 5060 | 5060 | 25300 | 0 | 0 | 0 | 0 | 0 | 0 | 25300 | 10320 | 10320 | 10320 | 10320 | 10320 | 51600 | 0 | 0 | 0 | 0 | 0 | 0 | 51600 | 6.769% | 6.682%
Miles of roadway requiring sweeping (above x 2 times/yr) | 134 | [14 empty] | YR1 | YR2 | YR3 | YR4 | YR5 | [8 empty] | YR1 | YR2 | YR3 | YR4 | YR5
[15 empty] | Town MS4 Permit Tasks | 58119.0392 | 103588.4346 | 35856.817 | 89677.7778 | 30477.7778 |  | YR1 | YR2 | YR3 | YR4 | YR5 |  |  | 156560.0392 | 184863.6274 | 77387.7744 | 135208.7352 | 64808.7352 |  | YR1 | YR2 | YR3 | YR4 | YR5
[15 empty] | Consultant MS4 Permit Tasks | 0 | 0 | 0 | 0 | 0 |  | 68247.0392 | 115066.4346 | 47334.817 | 101155.7778 | 41955.7778 |  |  | 0 | 0 | 0 | 0 | 0 |  | 184338.6272 | 216267.2154 | 108791.3624 | 166612.3232 | 96212.3232
TMDL / Impaired Water Bodies | [14 empty] | Intermittent (Town & Consultant) | 2800 | 4150 | 4150 | 4150 | 4150 |  |  |  | 5 Yr Program Cost Estimate (Low) | 373759.8463 |  |  |  | 13140.588 | 16765.588 | 16765.588 | 16765.588 | 16765.588 |  |  |  | 5 Yr Program Cost Estimate (High) | 772221.8514
Number of nitrogen TMDL water bodies | 11 | [13 empty] | Impaired Waters (Town & Consultant) | 7328 | 7328 | 7328 | 7328 | 7328 |  |  |  | Potential Truck Purchase / Replacement Cost | 250000 |  |  |  | 14638 | 14638 | 14638 | 14638 | 14638 |  |  |  | Potential Truck Purchase / Replacement Cost | 570000
Number of nitrogen impaired water bodies | 0 | [14 empty] | Annual Low Estimated Costs to Town | [12 empty] | Annual High Estimated Costs to Town
Number of phosphorus impaired water bodies | 0
Number of bacteria impaired water bodies | 11 |  |  | Permit Year |  |  |  |  | # Yrs | % Complete | Estimated Hours |  | Work Distribution |  |  | Total Low Cost Estimate | [12 empty] | Total High Cost Estimate
|  |  | Intermittent Costs | [12 empty] | Annual Low Cost Estimates for Town | [5 empty] | Annual Low Cost Estimates for Consultant | [6 empty] | Annual High Cost Estimates for Town | [5 empty] | Annual High Cost Estimates for Consultant
|  |  |  | 1 | 2 | 3 | 4 | 5 |  |  | Low | High | Town | Region | Consultant | YR1 | YR2 | YR3 | YR4 | YR5 | Town | YR1 | YR2 | YR3 | YR4 | YR5 | Consultant | 5-Yr Total | YR1 | YR2 | YR3 | YR4 | YR5 | Town | [5 empty] | Consultant | 5-Yr Total
208 Credit |  |  | MCM3 - IDDE | [7 empty] | 0 | 400 | [8 empty] | 0 | [5 empty] | 0 | 0 | [5 empty] | 41702.94 | [5 empty] | 0 | 41702.94
For nitrogen-impaired water bodies: the following additional control measures |  |  | Update mapping for new construction | x | x | x | x | x | 5 | 0% | 0 | 200 | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 4000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
may be applied toward the 25% reduction in nitrogen in stormwater |  |  | Follow up sampling for illicit discharge source ID | x | x | x | x | x | 5 | 0% | 0 | 80 | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1883.8233 | 1883.8233 | 1883.8233 | 1883.8233 | 1883.8233 | 9419.1167 | 0 | 0 | 0 | 0 | 0 | 0 | 9419.1167
Conducting nitrogen related public outreach |  |  | Identify responsible parties | x | x | x | x | x | 5 | 0% | 0 | 40 | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 800 | 800 | 800 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
Making nitrogen removal a priority for retrofit rankings |  |  | Confirmatory wet weather sampling after removal | x | x | x | x | x | 5 | 0% | 0 | 80 | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1656.7647 | 1656.7647 | 1656.7647 | 1656.7647 | 1656.7647 | 8283.8233 | 0 | 0 | 0 | 0 | 0 | 0 | 8283.8233
Optimize stormwater BMPs for nitrogen removal |  |  | MCM4 - Construction Site Control | [7 empty] | 140 | 240 | [8 empty] | 14000 | [5 empty] | 0 | 14000 | [5 empty] | 24000 | [5 empty] | 0 | 24000
Using slow-release fertilizer on municipal properties |  |  | Pre-construction peer review | x | x | x | x | x | 5 | 0% | 120 | 200 | 100% |  |  | 2400 | 2400 | 2400 | 2400 | 2400 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 4000 | 4000 | 4000 | 4000 | 4000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
Enhancing clean up of leaf litter |  |  | Construction site inspections | x | x | x | x | x | 5 | 0% | 20 | 40 | 100% |  |  | 400 | 400 | 400 | 400 | 400 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 800 | 800 | 800 | 800 | 800 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
Conducting well timed municipal street sweeping |  |  | MCM6 - Good Housekeeping | [7 empty] | 0 | 52 | [8 empty] | 5400 | [5 empty] | 0 | 5400 | [5 empty] | 14500 | [5 empty] | 0 | 14500
|  |  | Investigate catchments with excess sediment |  | x | x | x | x | 4 | 0% | 0 | 12 | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 300 | 300 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 1200
Community Notes / Assumptions |  |  | Document catchment investigations |  | x | x | x | x | 4 | 0% | 0 | 40 | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
|  |  | Repair and replace SWPPP control measures (assumed 20% of SWPPP implementation) |  | x | x | x | x | 4 | 0% | 0 | 0 | 100% |  |  | 0 | 1350 | 1350 | 1350 | 1350 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 2325 | 2325 | 2325 | 2325 | 9300 | 0 | 0 | 0 | 0 | 0 | 0 | 9300
|  |  |  | Permit Year |  |  |  |  | # Yrs | % Complete | Estimated Hours |  | Work Distribution |  |  | Total Low Cost Estimate | [12 empty] | Total High Cost Estimate
|  |  | Impaired Water Bodies | [12 empty] | Annual Low Cost Estimates for Town | [5 empty] | Annual Low Cost Estimates for Consultant | [6 empty] | Annual High Cost Estimates for Town | [5 empty] | Annual High Cost Estimates for Consultant
|  |  | Nitrogen TMDL or N/P Impaired Water | 1 | 2 | 3 | 4 | 5 |  |  | Low | High | Town | Region | Consultant | YR1 | YR2 | YR3 | YR4 | YR5 | Town | YR1 | YR2 | YR3 | YR4 | YR5 | Consultant | 5-Yr Total | YR1 | YR2 | YR3 | YR4 | YR5 | Town | [5 empty] | Consultant | 5-Yr Total
Town Total Number of ERU | 9162 |  | Enhanced BMPs | [7 empty] | 107.8 | 188.2 | [8 empty] | 36080 | [5 empty] | 0 | 36080 | [5 empty] | 69500 | [5 empty] | 0 | 69500
| $ / ERU | 5-year Revenue | Public Education (assumed add'l 10% of MCM1) | x | x | x | x | x | 5 | 0% | 11.2 | 73 | 100% |  |  | 224 | 224 | 224 | 224 | 224 | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 1120 | 1476 | 1476 | 1476 | 1476 | 1476 | 7380 | 0 | 0 | 0 | 0 | 0 | 0 | 7380
National Average ERU rate ($5.18) | 5.18 | 2847549.6 | Post Construction Site Control (assumed add'l 10% of MCM5) | x | x | x | x | x | 5 | 0% | 62.2 | 76.4 | 100% |  |  | 1304 | 1304 | 1304 | 1304 | 1304 | 6520 | 0 | 0 | 0 | 0 | 0 | 0 | 6520 | 1648 | 1648 | 1648 | 1648 | 1648 | 8240 | 0 | 0 | 0 | 0 | 0 | 0 | 8240
National Median ERU rate ($4.00) | 4 | 2198880 | Good Housekeeping (assumed add'l 10% of MCM6 O&M) | x | x | x | x | x | 5 | 0% | 34.4 | 38.8 | 100% |  |  | 688 | 688 | 688 | 688 | 688 | 3440 | 0 | 0 | 0 | 0 | 0 | 0 | 3440 | 776 | 776 | 776 | 776 | 776 | 3880 | 0 | 0 | 0 | 0 | 0 | 0 | 3880
Town Specified ERU rate | 3 | 1649160 | Street Sweeping 2x / yr | x | x | x | x | x | 5 | 0% | 0 | 0 | 100% |  |  | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
| Low Estimate | High Estimate | N or P Source ID Report (assumed 25% of catchment assessment / ranking per water body) | x | x | x | x |  | 4 | 0% | 0 | 0 | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Monthly ERU rate to fund 100% of budget (low / high range) | 0.67991 | 1.4048 | Bacteria TMDL / Impaired Water
Annual household cost to fund 100% of budget | 8.1589 | 16.8571 | Enhanced BMPs | [7 empty] | 11.2 | 73 | [8 empty] | 560 | [5 empty] | 0 | 560 | [5 empty] | 3690 | [5 empty] | 0 | 3690
|  |  | Public Education (assumed add'l 5% of MCM1) | x | x | x | x | x | 5 | 0% | 11.2 | 73 | 100% |  |  | 112 | 112 | 112 | 112 | 112 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 560 | 738 | 738 | 738 | 738 | 738 | 3690 | 0 | 0 | 0 | 0 | 0 | 0 | 3690
LEGEND: CELL COLORS
User can fill in or otherwise edit this cell.
Spreadsheet generates calculation based on filled-in cells.
Spreadsheet output, based on user-provided information and EPA cost estimator.

## Tasks by Year
Permit Year
Permit Task | 1 | 2 | 3 | 4 | 5 | 6+
Notice of Intent | X
SWMP | X
MCM1 Public Education | X | X | X | X | X | X
MCM2 Public Participation | X | X | X | X | X | X
MCM3 IDDE
Written IDDE Plan / Procedures | X
System Mapping / Catchment Delineation | X | X | X | X | X | X
Catchment Assessment / Ranking | X | x | x
Dry Weather Screening | X | X | X
Wet Weather Screening |  |  | X | X | X | X
Catchment Investigations |  | X | X | X | X | X
Training | X | X | X | X | X | X
MCM 4 - Construction Site Control
Update of construction bylaw/ordinance | x
Construction review / site inspection procedures | x
Preconstruction reviews | x | x | x | x | x | x
Construction site inspections | x | x | x | x | x | x
MCM 5 - Post Construction Site Control
Update post construction regulations |  | X
Report on existing street / parking regulations |  |  |  | X
Inventory municipal properties |  |  |  | X
MCM 6 - Good Housekeeping
Develop Operation / Maintenance Procedures |  | x
BMP Inspection / Maintenance |  | x
SWPPP Written Plan Preparation |  | x
SWPPP Implementation |  | x | x | x | x
Catch Basin Cleaning | x | x | x | x | x | x
Street Sweeping | x | x | x | x | x | x
Training | x | x | x | x | x | x
Annual Report | x | x | x | x | x | x

## Overview of Total Costs
Overview of Total Cost of Program (over 5 years) | [5 empty] | Overview of Annual Cost of Program
Minimum Control Measure |  | Cost |  | Hours |  | Minimum Control Measure |  | Cost |  | Hours
|  | Low | High | Low | High |  |  | Low | High | Low | High
Public Education |  | 11200 | 73800 | 112 | 730 | Public Education |  | 2240 | 14800 | 22.4 | 146
Public Participation |  | 9000 | 17000 | 80 | 150 | Public Participation |  | 1800 | 3400 | 16 | 30
Good Housekeeping | rented trucks | 176000 | 290000 | 737 | 1080 | Good Housekeeping | rented trucks | 35200 | 58000 | 147 | 216
| purchased trucks | 404000 | 816000 | 737 | 1080 |  | purchased trucks | 80800 | 163000 | 147 | 216
NOI |  | 5000 | 11200 | 50 | 112 | NOI |  | 1000 | 2240 | 10 | 22.4
SWMP |  | 12800 | 20400 | 128 | 204 | SWMP |  | 2560 | 4080 | 25.6 | 40.8
IDDE |  | 48500 | 138000 | 460 | 1330 | IDDE |  | 9700 | 27600 | 92 | 266
Construction Site Control |  | 4200 | 21600 | 32 | 96 | Construction Site Control |  | 840 | 4320 | 6.4 | 19.2
Post Construction Site Control |  | 65200 | 82400 | 622 | 764 | Post Construction Site Control |  | 13000 | 16500 | 124 | 153
Annual Report |  | 25300 | 51600 | 253 | 516 | Annual Report |  | 5060 | 10300 | 50.6 | 103
Total | rented trucks | 357000 | 706000 | 2470 | 4980 | Total | rented trucks | 71400 | 141000 | 494 | 996
| purchased trucks | 585000 | 1230000 | 2470 | 4980 |  | purchased trucks | 117000 | 246000 | 494 | 996

## Public Education
Task Specific Multipliers
Consultant Rate |  | 100
# of residents |  | 6125
Assumed # of households |  | 3025
| Cost |  | Hours
| Low | High | Low | High
Annual | 1400 | 9300 | 14 | 92
One-Time | 2400 | 3000 | 24 | 30
Intermittent | 0 | 0 | 0 | 0
Total | 11200 | 73800 | 112 | 730
No. | Type of Action | Time from Effective Date | Frequency | Permit Deliverable | Public Education and Outreach Requirement | Reference | Type of Material | One Time Costs |  |  |  | Annual/Ongoing Costs |  |  |  |  | Total Costs/Hours |  |  |  | Notes | Supporting Documentation
[8 empty] | Hours |  | Fixed Cost |  | Hours per Year |  | Fixed Cost |  | Number of Years | Total Cost Over 5-Year Permit Period |  | Total Hours over 5-year period
[8 empty] | Low | High | Low | High | Low | High | Low | High |  | Low | High | Low | High
1 | Admin |  | Annual - Ongoing |  | Continue public education program required by 2003 permit. | 2.3.2 a | [14 empty] | This will be covered by other requirements of the permit.
2 | Admin | 1 year | One-time |  | Develop program - Define goals, express specific messages define audience for each message, identify parties responsible for implementation, identify methods to evaluate effectiveness of messages. | 2.3.2 a |  | 24 | 30 | [6 empty] | 1 | 2400 | 3000 | 24 | 30 | Assume 24-30 hours one time cost for meeting and coordination time with the community to determine what they currently do and what works for them in the future. | WV estimate
2.1 | Admin | Begin 1st year of permit | Annual |  | Develop and send out two separate messages for each of 4 different audiences (residential, business/commercial/institution, developer & construction, industrial) - assume distribution annually and a total of 8 messages per permit term. | 2.3.2 c | Mailed Brochure |  |  |  |  | 6 | 8 | 151.25 | 302.5 | 1 | 751.25 | 1102.5 | 30 | 40 | Assume 6-8 hours per year for development of brochure; printing and mailing costs range from $0.05 -$0.10 per household (assume approximately 6,000 households) | WV estimate and current copy rates
[7 empty] | Printed Flyer |  |  |  |  | 6 | 8 |  |  | 1 | 600 | 800 | 30 | 40 | Assume 6-8 hours per year for development of flyer | WV estimate
[7 empty] | Website |  |  | 2500 | 5000 | 4 | 8 |  |  | 1 | 2900 | 5800 | 20 | 40 | Assume website start up cost of $2,500-$5,000 and annual maintenance cost of 4-8 hours | WV estimate
[7 empty] | Workshops |  |  |  |  | 32 | 80 | 50 | 100 | 1 | 3250 | 8100 | 160 | 400 | Hours include time for advertising, reaching out to businesses, preparing workshops and materials. Additional costs are based on materials to be printed for workshops. | WV estimate
[16 empty] | Total Cost | 4800 | 64800 | 48 | 640 | Range based on assumption a community will do the least expensive (flyers) task or the most expensive task (workshops) for a total of 8 messages throughout the permit term. | WV estimate
2.2 | Admin |  | Annual |  | Review program and modify ineffective messages or distribution techniques. | 2.3.2 f | [5 empty] | 8 | 12 |  |  | 5 | 4000 | 6000 | 40 | 60 | Assume this is just a summary and modification where needed. | WV estimate
2.3 | Admin |  | Annual | x | Document program in annual report: messages for each audience; method of distribution; measures/methods used to assess effectiveness of message; measures/methods to assess effectiveness. | 2.3.2 g | [14 empty] | Most costs will go towards measuring effectiveness; estimated in annual report tab | WPI report estimate $8,820 to assess effectiveness of program (annual).
[16 empty] | TOTAL FOR FIVE YEARS | 11200 | 73800 | 112 | 730 |  | WPI report estimate $10K-$20K for MA communities; CA cost survey estimated $28K-$350K annual cost for program

## Public Participation
Task Specific Multipliers
Consultant Rate |  | 100
| Cost |  | Hours
| Low | High | Low | High
Annual | 1800 | 3400 | 16 | 30
One-Time | 0 | 0 | 0 | 0
Intermittent | 0 | 0 | 0 | 0
Total | 9000 | 17000 | 80 | 150
No. | Type of Action | Time from Effective Date | Frequency | Permit Deliverable | Public Involvement and Participation Requirement | Reference | One Time Costs |  |  |  | Annual/Ongoing Costs |  |  |  |  | Total Costs/Hours |  |  |  | Notes | Supporting Documentation
[7 empty] | Hours |  | Fixed Cost |  | Hours per Year |  | Fixed Cost |  | Number of Years | Total Cost Over 5-Year Permit Period |  | Total Hours Over 5-Year Permit Period
[7 empty] | Low | High | Low | High | Low | High | Low | High |  | Low | High | Low | High
1 | Admin |  | Annual - Ongoing |  | Comply with state public Notice requirements. Make SWMP & annual reports available to public. | 2.3.3 a |  |  |  |  | 8 | 16 |  |  | 5 | 4000 | 8000 | 40 | 80 | Most municipalities will continue to follow current town public notice requirements. May include posting SWMPs, annual reports, and other information about the permit to an already established town website or bulletin board. | WV estimate
2 | Admin |  | Annual - Ongoing |  | Provide annual opportunity for public to participate in review and implementation of SWMP. May include websites, hotlines, clean-up teams, monitoring teams, advisory committee. | 2.3.3 b |  |  |  |  | 8 | 14 | 200 | 400 | 5 | 5000 | 9000 | 40 | 70 | Assume most municipalities will use current town forums including town meetings and updating websites. | WV estimate
3 | Admin |  | Annual - Ongoing | x | Report activities in annual report. | 2.3.3 c | [8 empty] | 5 | 0 | 0 | 0 | 0 | In annual report tab
4 | Admin |  | Annual - Ongoing |  | Keep records for 5 years. | 4.2.a | [13 empty] | Covered under annual reporting
5 | Admin |  | Annual - Ongoing |  | Make records relating to the permit available to the public. | 4.2.c | [13 empty] | Covered under other public notification requirements (2.3.3 a)
[15 empty] | TOTAL FOR FIVE YEARS | 9000 | 17000 | 80 | 150 |  | Weston and Sampson cost estimate for Merrimack Valley Planning Commission $500-$5K annual

## Good Housekeeping
Task Specific Multipliers
Structures needing annual cleaning |  | 154.6
Number of Curb Miles |  | 134
Number of Outfalls |  | 12
Number of Facilities |  | 65
Number of BMPs |  | 3
Number of facilities requiring SWPPPs |  | 3 | 3
Consultant Rate |  | 100
Rented Truck
| Cost |  | Hours
| Low | High | Low | High
Annual | 25100 | 46600 | 77 | 132
One-Time | 50200 | 55400 | 352 | 404
Intermittent | 0 | 5200 | 0 | 52
Total* | 176000 | 290000 | 737 | 1080
*Without Intermittent Costs
Purchased Truck
| Cost |  | Hours
| Low | High | Low | High
Annual | 20700 | 38100 | 77 | 132
One-Time | 300000 | 625000 | 352 | 404
Intermittent | 0 | 5200 | 0 | 52
Total* | 404000 | 816000 | 737 | 1080
*Without Intermittent Costs
No. | Type of Action | Time from Effective Date | Frequency | Permit Deliverable | Pollution Prevention and Good Housekeeping Requirement | Reference | One Time Costs |  |  |  | Annual/Ongoing Costs |  |  |  |  | Total Costs/Hours |  |  |  | Notes | Supporting Documentation
[7 empty] | Hours |  | Fixed Cost |  | Hours per Year |  | Fixed Cost |  | Number of Years | Total Cost Over 5-Year Permit Period |  | Total Hours Over 5-Year Permit Period
[7 empty] | Low | High | Low | High | Low | High | Low | High |  | Low | High | Low | High
1 |  |  |  |  | Develop Facility O&M Procedures
1.1 | Admin | 1 year | One-time |  | Develop an inventory of all permittee owned facilities within the following categories: parks & open space, buildings & facilities, vehicles & equipment. | 2.3.7 a ii | 16 | 20 | [6 empty] | 1 | 1600 | 2000 | 16 | 20 | Assume 12 hours for site visits and 4-8 hours to prep table/report/letter | WV estimate
1.2 | Admin | 1 year | One-time |  | Develop or update written O&M procedures for listed municipal facilities. | 2.3.7 a i | 268 | 268 | [6 empty] | 1 | 26800 | 26800 | 268 | 268 | Develop template and general procedures for all facilities (8 hours); develop procedures for all listed facilities (each facility = 4 hours) | Weston and Sampson Cost estimate for Merrimack Valley Planning Commission ($5K-$10K)
1.3 |  |  | Annual |  | Review inventory annually and update as necessary. | 2.3.7 a ii |  |  |  |  | 8 | 8 |  |  | 5 | 4000 | 4000 | 40 | 40 |  | WV estimate
2 |  |  |  |  | Develop Infrastructure O&M Procedures
2.1 |  |  |  |  | Catch Basin Cleaning
2.1.1 | Tech | 1 year | One-time - updated as needed |  | Develop a written optimization plan detailing procedures and schedule for cleaning and maintaining catch basins to ensure no catch basin is more than 50% full. Include inspection and maintenance prioritization. | 2.3.7 a iii b | 24 | 36 | [6 empty] | 1 | 2400 | 3600 | 24 | 36 | Includes hours to work with town to develop specifically for their system and develop GIS map and tracking tool. | WV estimate
2.1.2 | Maint |  | Annual |  | Clean catch basins (rented truck) | 2.3.7 a iii b | [6 empty] | 7730 | 15460 | 5 | 38650 | 77300 | 0 | 0 | Assumes rented truck ($50-$100 per structure) | See accompanying word doc
|  |  | One-Time |  | Clean catch basins (purchased truck). | 2.3.7 a iii b |  |  | 125000 | 320000 |  |  | 5000 | 10000 | 1 | 150000 | 370000 | 0 | 0 | Truck purchase = $125,000-$320,000; annual cost for gas, maintenance, insurance; assumes driver's salary is already covered by existing budget) | Pennichuck Brook Watershed Feasibility Study
2.1.3 | Maint |  | Intermittent |  | If more than 50% full during two routine cleanings, investigate the cause for excessive sediment loading. | 2.3.7 a iii b |  |  |  |  | 0 | 2.4 |  |  | 5 | 0 | 1200 | 0 | 12 | Investigation will likely involve driving around the subcatchment area to identify construction or sources of erosion, therefore, level of effort can be tied to number of outfalls. Assume up to 20% of outfalls have sediment issues and 1 hour per investigation. | WV estimate
2.1.4 | Admin |  | Intermittent |  | Describe actions taken to assess and abate catch basins that are more than 50% full during two consecutive cleanings. | 2.3.7 a iii b |  |  |  |  | 0 | 8 |  |  | 5 | 0 | 4000 | 0 | 40 | Assume basic report. | WV estimate
2.1.5 | Admin/Tech | 1 year | One-time | x | Document in first annual report the plan for optimizing catch basin cleaning, inspections or scheduling. | 2.3.7 a iii b | 8 | 16 | [6 empty] | 1 | 800 | 1600 | 8 | 16 | Most work completed under PAI 2.1.1 and this would be a simple write up
2.1.6 | Maint |  | Annual |  | Maintain a log of catch basins cleaned or inspected. | 2.3.7 a iii b |  |  |  |  | 16 | 24 |  |  | 5 | 8000 | 12000 | 80 | 120
2.1.7 | Admin |  | Annual | x | In each annual report list the total number of catch basins, number inspected and/or cleaned, and the volume or mass of material removed from each catch basin draining to water quality limited waters and the total volume or mass of material removed from all catch basins. | 2.3.7 a iii b | [8 empty] | 5 | 0 | 0 | 0 | 0 | Material for report should be available through 2.1.2. and 2.1.6. Hours to assemble report and calculate material removed ( 8 hours in annual report tab)
2.2 |  |  |  |  | Street Sweeping
2.2.1 | Tech | 1 year | One-time |  | Develop and implement procedures for sweeping streets and municipal-owned lots. Include more frequent sweeping of targeted areas determined by the permittee on the basis of pollutant load reduction potential, based on inspections, pollutant loads, catch basin cleaning or inspection results, land use, water quality limited or RMDL waters or other relevant factors as determined by the permittee. | 2.3.7 a iii c | 16 | 24 | [6 empty] | 1 | 1600 | 2400 | 16 | 24 | Includes hours to work with town to develop specifically for their system and develop GIS map and tracking tool. | WV estimate
2.2.2 | Maint |  | Annual |  | Sweep all streets (rural exceptions apply) a minimum of once a year in the spring. | 2.3.7 a iii c | [6 empty] | 6700 | 13400 | 5 | 33500 | 67000 | 0 | 0 | Assumes rented truck ($50-$100 per curb mile) | See accompanying word doc
|  |  | One-time |  | Sweep all streets (rural exceptions apply) a minimum of once a year in the spring. | 2.3.7 a iii c |  |  | 125000 | 250000 |  |  | 5000 | 10000 | 1 | 150000 | 300000 | 0 | 0 | Truck purchase = $125,000-$250,000; annual cost for gas, maintenance, insurance; assumes driver's salary is already covered by existing budget.
2.2.3 | Admin |  | Annual | x | Each annual report shall include number of miles cleaned and volume or mass of material removed. | 2.3.7 a iii c | [8 empty] | 5 | 0 | 0 | 0 | 0 | in annual report tab
2.2.4 | Maint |  | Annual | x | For rural exception areas, either sweep once each spring, or develop specific procedures and place in first annual report. | 2.3.7 a iii c | 0 | 20 |  |  | 0 | 10 |  |  | 5 | 0 | 7000 | 0 | 70 | Most communities will already be sweeping all roads. For rural communities, costs include 20 hours to develop plan and additional 10 hours per year to conduct a windshield survey and document. | WV estimate
2.2.5 | Maint |  | Ongoing |  | Properly store & dispose of catch basin cleanings and street sweepings so they do not discharge to receiving waters. | 2.3.7 a iii d | [8 empty] | 5 | 0 | 0 | 0 | 0 | No cost as storage and disposal are regulated elsewhere. If truck is rented, disposal costs are included. | WV estimate
2.3 |  |  |  |  | Winter Road Maintenance
2.3.1 | Tech | 1 year | One-time |  | Establish written procedures for winter road maintenance including storage of salt and sand; minimize use of sodium chloride and other salts; ensure snow disposal activities do not result in disposal of snow into surface waters. | 2.3.7 a iii e | 8 | 16 | [6 empty] | 1 | 800 | 1600 | 8 | 16 |  | WV estimate
2.3.2 | Maint |  | Annual |  | Implement procedures for winter road maintenance. | 2.3.7 a iii e | [8 empty] | 5 | 0 | 0 | 0 | 0 | Minimal cost as winter road maintenance costs are likely factored elsewhere. | WV estimate
2.4 |  |  |  |  | Maintenance of Town-owned Stormwater Treatment Structures
2.4.1 | Tech | 1 year | One-time |  | Establish written O&M procedures for all permittee-owned stormwater BMPs (e.g., swales, retention basins etc.). | 2.3.7 a iii f | 12 | 24 | [6 empty] | 1 | 1200 | 2400 | 12 | 24 | Assume 8 hours for general procedures and 4-16 for specific BMPs. | WV estimate
2.4.2 | Maint |  | Annual |  | Inspect all such structures at least once annually. | 2.3.7 a iii f |  |  |  |  | 9 | 12 |  |  | 5 | 4500 | 6000 | 45 | 60 | Assume 1-2 hours per BMP and 6 hours for documentation | WV estimate
2.4.3 | Admin |  | Annual | x | Report in the annual report on the status of all O&M activities. | 2.3.7 a iv | [8 empty] | 5 | 0 | 0 | 0 | 0 | in annual report tab
2.4.4 | Admin |  | Ongoing |  | Keep a written record of all required activities. | 2.3.7 a v | [8 empty] | 5 | 0 | 0 | 0 | 0 | Cost included throughout other items. | WV estimate
3 |  |  | SWPPP
3.1 | Tech | 2 years | One-time |  | Develop a SWPPP for maintenance garages, public works yards, transfer stations, and other waste handling facilities where pollutants are exposed to stormwater. | 2.3.7 b |  |  | 15000 | 15000 |  |  |  |  | 1 | 15000 | 15000 | 0 | 0 | Assume $5,000 per facility. SWPPPs are required for3-5 of the 10 regulated facilities. | CA State Water Board $5K-$10K per SWPPP
3.2 | Tech/Maint | 2 years | Annual |  | Fully implement SWPPPs for each of the listed facilities. | 2.3.7 b | [6 empty] | 3000 | 4500 | 5 | 15000 | 22500 | 0 | 0 | Costs will vary based on extent of SWPPPs; assume approximately $1,000-$1,500 per facility (3-5 facilities annually) | CA State Water Board $1K per facility
3.3 | Admin/Tech |  | Annual |  | Regularly train employees who work in areas where materials or activities are exposed to stormwater. Document training date, title and duration; attendees; subjects covered during training. | 2.3.7 d 8 |  |  |  |  | 12 | 14 |  |  | 5 | 6000 | 7000 | 60 | 70 | Assume one annual training (8 hours) and 4-6 hours for documentation and prep | WV estimate
3.4 | Tech/Maint |  | Quarterly |  | Inspect all areas exposed to stormwater and all stormwater control measures at least every calendar quarter, with one when a stormwater discharge is occurring. | 2.3.7 b iii a |  |  |  |  | 24 | 48 |  |  | 5 | 12000 | 24000 | 120 | 240 | Assume 2-4 hours per facility (3-5 facilities) per quarter or 8-16 hours per facility per year | WV estimate
3.5 | Maint |  | Intermittent |  | Repair or replace any control measures needing repair before the next anticipated storm event. | 2.3.7 b iii a | [8 empty] | 5 | 0 | 0 | 0 | 0 | No costs estimated as it could range from $0 - ? Based on extent of problem. | WV estimate
3.6 | Admin |  | Annual | x | Report the findings from the Site inspections in the annual report. | 2.3.7 b iii a | [8 empty] | 5 | 0 | 0 | 0 | 0 | in annual report tab
3.7 | Admin |  | Ongoing |  | Keep a written record of all required activities required under the SWPPP. | 2.3.7 b iv |  |  |  |  | 8 | 16 |  |  | 5 | 4000 | 8000 | 40 | 80 |  | WV estimate
[15 empty] | TOTAL FOR FIVE YEARS Rented Truck (W/o Intermittent Costs) | 176000 | 290000 | 737 | 1080
[15 empty] | TOTAL FOR FIVE YEARS Purchased Truck (W/o Intermittent Costs) | 404000 | 816000 | 737 | 1080

## NOI
Task Specific Multipliers
Consultant Rate |  | 100
| Cost |  | Hours
| Low | High | Low | High
Annual | 0 | 0 | 0 | 0
One-Time | 5000 | 11200 | 50 | 112
Intermittent | 0 | 1600 | 0 | 16
Total | 5000 | 11200 | 50 | 112
*Without Intermittent Costs
No. | Type of Action | Time from Effective Date | Frequency | Permit Deliverable | NOI Requirement |  | One Time Costs |  |  |  | Annual/Ongoing Costs |  |  |  |  | Total Costs/Hours |  |  |  | General Notes | Supporting Documentation
[6 empty] | Reference | Hours |  | Fixed Costs |  | Hours per Year |  | Fixed Costs |  | Number of Years | Total Cost Over 5-Year Permit Period |  | Total Hours Over 5-Year Permit Period
[7 empty] | Low | High | Low | High | Low | High | Low | High |  | Low | High | Low | High
1 |  | 90 days |  | x | Prepare and Submit NOI | 1.7.2
1.1 |  | 90 days |  |  | Document Endangered Species | 1.9.1
1.1.1 | Admin | 90 days | One-time |  | Step 1 - Complete Information, Planning and Conservation (IPaC) online system process to determine if federally listed species or designated critical habitats are present in the area. If not present (i.e., meet Criterion A), skip to Step 4, otherwise go to Step 2. | Appendix C. B.1. Step 1 | 4 | 4 | 0 |  | 0 |  | 0 |  | 0 | 400 | 400 | 4 | 4 | Assume 4 hours to query online system and document in letter report. | WV estimate
1.1.2 | Technical | 90 days | One-time |  | Step 2A - Review potential impacts of discharges to species/habitats to determine if your discharges have "no affect", "may affect" or are "not likely to adversely affect" species/habitat. If you determine "may affect" or "not likely to adversely affect", go to Step 2B, otherwise go to Step 3. | Appendix C. B.1. Step 2 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Combine with Step 2B. | WV estimate
1.1.3 | Technical | 90 days | One-time |  | Step 2B - Contact USFWS for consultation and opinion. If opinion is "no jeopardy" or you receive concurrence that discharges are "not likely to adversely affect", and you agree to implement all measures upon which the consultation was conditioned and you agree to re-initiate consultation with USFWS as necessary, skip to Step 4, otherwise go to Step 3. | Appendix C. B.1. Step 2 | 0 | 16 | 0 |  | 0 |  | 0 |  | 0 | 0 | 1600 | 0 | 16 | Assume 16 hours to review discharge locations in relation to query findings, phone conversation with USFWS, and brief letter report, follow-up correspondence and ultimate decision. Note this step may not be necessary pending Step 2A results. | WV estimate
1.1.4 | Technical | 90 days | One-time |  | Step 3 - If you determined there would be "no affect" on listed species, contact EPA to obtain concurrence with that determination. If they concur, agree to conduct an endangered species screening for proposed structural BMPs and contact USFWS as appropriate (e.g., new activity "may affect" or is "not likely to adversely affect"). If these conditions are met, you meet Criterion C and go to Step 4. Any other scenarios are not eligible for coverage under the MS4. | Appendix C. B.1. Step 3 | 0 | 10 | 0 |  | 0 |  | 0 |  | 0 | 0 | 1000 | 0 | 10 | Not likely, however, assume 10 hours for phone conversation and brief letter report, follow-up correspondence and ultimate decision. | WV estimate
1.1.5 | Admin | 90 days | One-time |  | Step 4 - Include documentation of USFWS ESA eligibility in the SWMP. | Appendix C. B.1. Step 4 | 2 | 2 | 0 |  | 0 |  | 0 |  | 0 | 200 | 200 | 2 | 2 | Assume 2 hours to incorporate results into written SWMP Plan. | WV estimate
1.2 |  | 90 days |  |  | Document Historic Properties Preservation | 1.9.2
1.2.1 | Admin | 90 days | One-time |  | Q1 - If the facility is an existing facility authorized by the previous permit or a new facility not undertaking any activity involving subsurface land disturbance less than an acre, then certify that fact in writing and file the statement with the EPA, otherwise go to Q2. | Appendix D, Screening Process, Question 1 | 4 | 4 | 0 |  | 0 |  | 0 |  | 0 | 400 | 400 | 4 | 4 | Assume 4 hours to prepare brief cover letter. Note: it is assumed that most facilities were authorized under the previous permit. | WV estimate
1.2.2 | Technical | 90 days | One-time |  | Q2A - Review National Register of Historic Places. If no properties listed, or discharges do not have the potential to cause effects on historic properties, then certify that fact in writing and file the statement with the EPA, otherwise go to Q2B. | Appendix D, Screening Process, Question 2 | 0 | 4 | 0 |  | 0 |  | 0 |  | 0 | 0 | 400 | 0 | 4 | Assume 4 hours to query National Register and document results in a brief letter report. | WV estimate
1.2.3 | Technical |  | Intermittent |  | Q2B - Initiate request for project review by SHPO - prepare Completed Project Notification Form, USGS map with area of concern, Scaled project plans showing existing and proposed conditions, photos where available. Include description of measures/conditions to be taken to avoid or minimize adverse impacts where applicable. | Appendix D, Screening Process, Question 2 | 0 | 0 | 0 |  | 0 | 16 | 0 |  | 1 | 0 | 1600 | 0 | 16 | Assume 8 hours for a consultant to prepare a PNF, USGS map and other information, and 8 hours to develop a list of conditions to avoid impacts. Note: Likely not required. | WV estimate
1.3 |  | 90 days |  | x | Complete NOI Form
1.3.1 | Admin | 90 days | One-time |  | Provide information on status of mapping and bylaws completed under 2003 permit. | Appendix E | 40 | 72 | 0 |  | 0 |  | 0 |  | 0 | 4000 | 7200 | 40 | 72 | Low - Assume 40 hours to meet with town (8), review impaired waters (8), review existing BMPs implemented under the 2003 permit (8), develop new BMPs to meet the six minimum measures under the new permit (12), and complete the NOI (4). High - Assume 72 hours to meet with town (8), review impaired waters (16), review existing BMPs implemented under the 2003 permit (16), develop new BMPs to meet the six minimum measures under the new permit (24), and complete the NOI (8). There would be cost savings to develop this in coordination with SWMP. | WV estimate
1.3.2 | Admin | 90 days | One-time |  | Provide summary of receiving waters - waterbody segment that receives flow from the MS4, number of outfalls into receiving water, impairment, pollutants causing impairment, whether there is a TMDL. | Appendix E
1.3.3 | Admin/Tech | 90 days | One-time |  | Identify new BMPs and goals to meet new permit. | Appendix E | [14 empty] | Haverhill MA: $7,200 to prepare all NOI PAIs.
[15 empty] | TOTAL FOR FIVE YEARS (W/O Intermittent Costs) | 5000 | 11200 | 50 | 112
50

## SWMP
Task Specific Multipliers
Consultant Rate |  | 100
| Cost |  | Hours
| Low | High | Low | High
Annual | 0 | 0 | 0 | 0
One-Time | 12800 | 20400 | 128 | 204
Intermittent | 0 | 0 | 0 | 0
Total | 12800 | 20400 | 128 | 204
No. | [7 empty] | One Time Costs |  |  |  | Annual/Ongoing Costs |  |  |  |  | Total Costs/Hours
| Type of Action | Time from Effective Date | Frequency | Permit Deliverable |  | SWMP Requirement | Reference | Hours |  | Fixed Cost |  | Hours per Year |  | Fixed Costs |  | Number of Years | Total Cost Over 5-Year Permit Period |  | Total Hours Over 5-Year Permit Period |  | General Notes | Supporting Documentation
[8 empty] | Low | High | Low | High | Low | High | Low | High |  | Low | High | Low | High
1 |  | 90 days | One-time |  | Prepare and Submit SWMP Plan |  | 1.7.2 | [14 empty] | -
1.1 | Tech | 120 days | One-time | x | Develop/update written SWMP to include: people responsible for program implementation; listing of all receiving waters, their classification, impairments, pollutants of concern, TMDLs, number of outfalls (included in NOI); surface drinking water supplies; listing of interconnected MS4; endangered species & historic properties documentation; documentation of authorization of new or increased discharges; map of MS4; practices to achieve compliance with TMDLs & non-TMDL impaired waters; practices to comply with six minimum measures; measures to avoid or minimize impacts to surface water supplies. |  | 1.10.a & 1.10.2 | 128 | 204 | 0 |  |  |  | 0 |  | 0 | 12800 | 20400 | 128 | 204 | Low - Assume 80 hours for preparation of written components, 40 hours for creation of maps and figures and 8 hours for meetings. High - Increase plan preparation to 120 hours, creation of maps and figures to 60 hours and meetings to 24 hours. | Haverhill MA: total cost of $14,400.
1.2 | Tech |  | Annual | x | Self-evaluate compliance with the terms and conditions of the permit including appropriateness of selected BMPs. |  | 4.1.a & b | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Performed under other annual report items. | -
[16 empty] | TOTAL FOR FIVE YEARS | 12800 | 20400 | 128 | 204

## IDDE
Task Specific Multipliers
Number of Outfalls |  | 12
Number of CBs (10 per outfall) |  | 773
Number of Key Junction Manholes
Option 1: 20% of CBs |  | 154.6
Option 2: 3 per outfall |  | 36
Number of outfalls flowing under dry conditions |  | 1.2
Percent of outfalls flowing under dry conditions |  | 0.1
Number of CA's with system vulnerability factors for wet weather sampling (25%) |  | 3
Number of CA's with system vulnerability factors for wet weather sampling (75%) |  | 9
Maximum number of illicit dicharge incidents. |  | 1
Consultant Rate |  | 100
Sample Analysis Cost (per sample - bacteria, ammonia, chlorine, salinity, surfactants) |  | 56.7647
Sample Analysis Multi-Meter (conductivity and temperature) |  | 469
| Cost |  | Hours
| Low | High | Low | High
Annual | 4500 | 10500 | 44 | 100
One-Time | 35600 | 101000 | 240 | 828
Intermittent | 0 | 43700 | 0 | 420
Total* | 48500 | 138000 | 460 | 1330
*Without Intermittent Costs
No. | Type of Action | Time from Effective Date | Frequency | Permit Deliverable | Illicit Discharge Detection and Elimination Requirement |  | Reference | One Time Costs |  |  |  | Annual/Ongoing Costs |  |  |  | Number of Years | Total Costs/Hours |  |  |  | Notes | Supporting Documentation
[8 empty] | Hours |  | Fixed Cost |  | Hours per Year |  | Additional Fixed Cost |  |  | Total Cost Over 5-Year Permit Period |  | Total Hours Over 5-Year Permit Period
[8 empty] | Low | High | Low | High | Low | High | Low | High |  | Low | High | Low | High
1 |  |  |  |  | Inventory Sanitary Sewer Overflows |  | 2.3.4.4
1.1 | Admin | 120 days | One-time |  | Identify and develop inventory of all known locations where SSOs have discharged to the MS4 in last 5 years. Include location, discharge to surface water or MS4, dates & time of each known SSO occurrence, volume, description of occurrence including cause, completed & planned mitigation & corrective measures with dates. |  | 2.3.4.4 b | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 24 | Most communities should know where their SSOs are located. Assume 24 hours for a consultant to compile existing SSO information and prepare a map. Note for many communities, this will be zero. | WV estimate
1.2 | Admin |  | Annual | x | Update inventory annually and report in annual report. |  | 2.3.4.4 b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Will be minimal. See Annual Report cost breakdown. | WV estimate
1.3 | Admin |  | Intermittent | x | Provide oral notice to EPA within 24 hours upon becoming aware of an SSO to the MS4. Provide written notice to EPA & MassDEP within 5 days, include inventory information. |  | 2.3.4.4 c | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 5 | 0 | 2000 | 0 | 20 | May not be required at all. Community dependent. Assume 4 hours for correspondence and brief letter report. Assume 1 notification per year over length of permit term. | WV estimate
2 |  |  |  |  | Develop Outfall Interconnection Inventory |  | 2.3.4.5
2.1 | Admin/Tech | 1 year | One-time |  | Identify each outfall & interconnection discharging from MS4, record location & condition. Include: unique identifier, receiving water, date of most recent inspection, dimensions, shape, material, lat/long, physical condition & indicators of non-stormwater discharges. |  | 2.3.4.5 c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Inventory will be compiled from combination of mapping and outfall screening performed under other PAIs, therefore no cost carried here. | WV estimate
2.2 | Admin |  | Annual | x | Update inventory annually to include data collected from monitoring program. |  | 2.3.4.5 b | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 5 | 0 | 8000 | 0 | 80 |  | WV estimate
2.3 | Maint | 5 years | One-time |  | Physically label all MS4 outfall pipes. |  | 2.3.4.5 b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Removed from permit. | WV estimate
3 |  |  |  |  | System Mapping |  | 2.3.4.6
3.1 | Tech | 2 years | One-time with annual upkeep |  | Develop a revised map of system showing outfalls & receiving waters (required by MS4 2003 permit), pipes, open channel conveyances, catch basins, manholes, interconnections, municipally-owned structure BMPs, and receiving waters by name (include indication of all impairments from 303(d) and 305(b) list). Map can be produced by hand or computer-aided methods. |  | 2.3.4.6 a i & 2.3.4.6 b | 130 | 556.56 | 0 | 1546 | 0 | 0 | 0 |  | 0 | 13000 | 57202 | 130 | 556.56 | Low cost is for generation of a paper map using existing available maps (e.g., subdivision maps) and uses the average of CWP hours. The map may not be 100% accurate and could be missing some structures if done this way. High costs assumes 2 field personnel at 25 structures per day. Also assumes another 2 hours per field day to pull data into GIS and map. Assume rental fee of $50/day for GPS unit. This also covers catchment investigations under PAI 4.4.4. See 4.3.2. for field investigation cost. | CWP IDDE Manual - 1 week to 4 weeks to gather outfall mapping information; 20 (paper) to 40 (GIS) hours to produce map. So total of between 60 and 200 hours. Holyoke: $60,000 for 3,300 CBs & MHs & 75 outfalls. Haverhill: $60,000 for 150 outfalls, unknown number of CBs and MHs.
3.2 | Tech | 2 years | One-time |  | Delineate catchment areas for each MS4 outfall or interconnection. |  | 2.3.4.6 a i | 4.8 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 8000 | 4.8 | 80 | Assumed number of catchment areas, same number as outfalls. Assume delineation of 20 outfalls per day in GIS. | Holyoke: $17,000 for 75 outfalls.
3.3 | Tech | 2 years | One-time with annual upkeep |  | Where available, include municipal sanitary sewer system & municipal combined sewer system. |  | 2.3.4.6 a ii | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 20 | Not required to map these from scratch, just include what it already mapped. Assume 0 for communities with nothing in GIS, minimal cost to overlay existing GIS layers with MS4 info. | WV estimate
3.4 | Tech | Not Required | Not Required |  |  | Recommended mapping elements - storm sewer material, size & age; sanitary sewer system material, size & age; properties served by septic (when sewer & septic exist); areas where MS4 could receive flow from septic systems (e.g., areas with poor soils, or high groundwater elevations); seasonal high water table elevation impacting sanitary alignments; topography; orthophotography; alignments; locations of illicit discharges | 2.3.4.6 a iii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Required so No Cost | WV estimate
3.5 | Tech |  | Intermittent |  | Update mapping as necessary to reflect newly discovered information & required corrections or modifications. |  | 2.3.4.6 b | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 5 | 0 | 20000 | 0 | 200 | Varies depending on the amount of new construction per year. Assume 0-40 hours per year to update map in GIS with new subdivision information. | Reese: 60 hours per year at $50/hour for large community.
3.6 | Admin |  | Annual | x | Report on progress of map in annual report. |  | 2.3.4.6 c | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See Annual Report cost breakdown | WV estimate
4 |  |  |  |  | Written IDDE Program |  | 2.3.4.7
4.1 | Admin | Required by 2003 Permit | One-time |  | Develop and adopt a regulatory mechanism providing legal authority to municipality to regulate illicit discharges. |  | 2.3.4.7 a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Required under 2003 Permit and should already be implemented. | Reese: 20 hours to adopt a generic ordinance for a town with 10,000 population. CWP IDDE Manual $1,000-$17,000.
4.2 | [5 empty] | Assessment & Priority Ranking of Catchments | 2.3.4.7 b
4.2.1 | Tech | 1 year initial, update annually | One-time |  | Assess and classify each catchment into one of 4 possible categories (Excluded, Problem, High Priority, Low Priority) |  | 2.3.4.7 c i | 24 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 4000 | 24 | 40 | Cost to delineate under PAI 3.2. Will depend on availability of classification factor information. Assume 24 hours minimum to collect data, develop a matrix and rank catchments. Increase up to 40 hours for more complex data. | WV estimate
4.2.2 | Tech | 1 year initial, update annually | One-time |  | Priority rank each catchment within each category (except those "excluded") using 8 factors (past complaints, poor dry weather receiving water quality, density of generating sites (e.g., car dealers, car washes, gas stations, garden centers, industrial, manufacturing), age of surrounding development & infrastructure, sewer conversion, historic combined sewer, density of aging septic systems, culverted streams. May also consider drinking water supplies, shell fishing areas, beaches or recreation waters, impaired waters. |  | 2.3.4.7 c ii & iii
4.2.3 | Tech |  | Annual | x | Update assessment & priority ranking annually based on results of screening and new information and include in annual report. Include listing of all catchments and results of ranking, summary of evidence of known or suspected illicit discharges and SSOs by catchment, corrective measures taken or planned, schedule for completing and verifying measures correcting the confirmed illicit discharges and SSOs. |  | 2.3.4.7 c iii | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 5 | 0 | 12000 | 0 | 120 | Varies depending on the amount of construction or newly identified outfalls per year and the amount of updated screening information. Assume 0-24 hours per year to update ranking with new information. | WV estimate
4.3 | [5 empty] | Outfall and Interconnection Screening and Sampling | 2.3.4.7 d
4.3.1 | Tech | 1 year | One-time |  | Develop written procedure for screening and sampling of outfalls - include sample collection, use of field kits, storage and conveyance of samples. Adopt a screening and sampling protocol consistent with EPA New England Bacterial Source Tracking Protocol (Draft 2012) (Appendix I). |  | 2.3.4.7 d i & ii | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Covered under 4.5.1.
4.3.2 | Tech | 3 years | One-time cost spread over a 3-year period |  | Perform dry weather screening of every outfall (if inaccessible, proceed to first accessible upstream structure) when and how prescribed; identify in annual report any follow-up needed. Begin investigations within 15 months of effective date. |  | 2.3.4.7 d iii & 2.3.4.8 a | 12 | 12 | 537.1176 | 537.1176 | 24 | 40 | 0 | 0 | 5 | 13737.1176 | 21737.1176 | 132 | 212 | Field mapping and dry weather sampling assumes 2 personnel per day at an average of 16 outfalls per day (based on CEI experience of performing outfall investigations). Equipment/lab includes one-time purchase of a multi-meter and field kits/lab tests for remaining parameters. Note: field efforts from PAI 2.1 combined with this PAI. Assume additional 24-40 hours for mapping and report preparation, which would include reporting for items PAI 4.3.2, 4.3.3 and 4.4.4. | CWP IDDE Manual - $9k-$21.2k per 80 samples for analysis only. Low assumes in-house analysis for Flow Chart Method & high assumes contracted lab analysis of 11 parameters. CWP's inspection costs were based on miles of stream rather than number of outfalls. This equates to $112.5-$265 per sample or $2,250-$5,300 for 20 samples. Haverhill: $31,500 to inspect 150 outfalls and sample 30 outfalls. Reese: $12,000 assuming 240 hours of student volunteers to screen outfalls.
4.3.2.A |  |  | Intermittent |  | Perform follow-up sampling to identify source if outfall sample comes back dirty. |  | 2.3.4.2 a | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 283.8233 | 5 | 0 | 9419.1167 | 0 | 80 | Permit just says to find source and remove. Assume there will be some follow-up sampling to do this. Assume a field crew of 2 people for 8 hours to investigate each incident, with up to 3 incidents per year. Assume an additional 5 samples per incident to help identify the source. | WV estimate
4.3.3 | Tech | 10 years | One-time cost spread over a 10-year period |  | Perform wet weather screening for outfalls with identified System Vulnerability Factors. |  | 2.3.4.7 d iv & 2.3.4.7 e ii b | 2.4 | 7.2 | 85.147 | 255.441 | 0 | 0 | 0 | 0 | 0 | 325.147 | 975.441 | 2.4 | 7.2 | Low assumes SVF applying to 25% of outfalls, high assumes 75%. Assume 5 outfalls per person per day. Note there can be substantial variation when performing wet weather sampling. To be completed as catchment investigations are completed, so assumed it was spread evenly over 10 years (e.g., represents half the total cost will occur in the first five years). Annual reporting and mapping costs included under PAI 4.3.2. | WV estimate
4.3.4 | Tech | see dry & wet weather screening schedules | One-time |  | Sample dry and wet weather flows for ammonia, chlorine, conductivity, salinity, E.coli (freshwater) or enterococcus (saline or brackish), surfactants, and temperature. All analyses with the exception of indicator bacteria can be performed with field test kits or field instrumentation. |  | 2.3.4.7 d v | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Included in 4.3.2 and 4.3.3. | WV estimate
4.3.5 | Admin |  | Annual | x | Report screening data annually; identify any follow-up needed. Include date, outfall ID, location, weather conditions, precipitation in previous 48 hours, field screening parameter results, and results of all analyses. |  | 2.3.4.8 a & 4.3.b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Costs included in other tasks. | WV estimate
4.4 | [5 empty] | Catchment Investigation Procedure | 2.3.4.7 e
4.4.1 | Tech | 1 year | One-time |  | Develop written Catchment Investigation Procedure including review of maps and historic records; a manhole inspection methodology; and procedures to isolate and confirm sources of illicit discharges. Include in written IDDE Plan. |  | 2.3.4.7 e | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Costs included under PAI 4.3.1 | WV estimate
4.4.2 | Tech | 1 year initial, update annually | One-time |  | Review sanitary sewer and storm sewer construction plans for each catchment. Identify and record the presence of System Vulnerability Factors: history of SSOs; areas that could readily result in SSOs; inadequate sanitary sewer level of service; common or twin-invert manholes serving storm & sanitary alignments; common trench construction serving both storm & sanitary; crossing of storm & sanitary; sanitary sewer with possible underdrain; sanitary sewer defects areas formerly served by combined sewer; sanitary sewer & storm drain infrastructure greater than 40 years old in medium and densely developed areas; widespread code-required septic upgrades; history of BOH actions addressing widespread septic failures. Include in IDDE Plan. |  | 2.3.4.7 e i | 16 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 4000 | 16 | 40 | Assume 16 hours for rural communities with no sewer to assess system vulnerability factors. Assume 40 hours for towns with sewer. | WV estimate
4.4.3 | Admin |  | Annual | x | Document and annually report presence or absence of the 12 System Vulnerability Factors for each catchment. |  | 2.3.4.7 e i | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See Annual Report cost breakdown | WV estimate
4.4.4 | Tech |  | One-time cost spread over a 10-year period |  | Perform dry weather investigation of key junction manholes by opening and inspecting for visual and olfactory evidence of illicit connections. |  | 2.3.4.7 e ii a & 2.3.4.8 c i,ii,iii | 35 | 9.6 | 500 | 750 | 0 | 0 | 0 | 0 | 0 | 4000 | 1710 | 35 | 9.6 | If a Town's system has not yet been mapped and will be through field mapping, then the costs will be covered under PAI 3.1. If the system is already mapped and only need to perform the catchment investigation, then use this cost. Costing assumes 20% of catch basins are KJMs as a low, or 3 per outfall for a high and covers investigation of all, which needs to be spread over 10 year period based on prioritization. Assume 30-40 structures per day with 2 field personnel. Additional annual reporting covered under PAI 4.3.2. Assume some additional funding for travel time and miscellaneous equipment. | WV estimate
|  | 3 years |  |  |  | *In a minimum of 80% of the MS4 area serviced by Problem Catchments within 3 years and 100% within 5 years | 2.3.4.8 c i |  |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
|  | 5 years |  |  |  | *For all catchments where sampling indicates sewer input within 5 years | 2.3.4.8 c ii |  |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
|  | 10 years |  |  |  | *In 40% of all area served by all MS4 catchments within 5 years and in 100% of 4 area in 10 years | 2.3.4.8 c iii |  |  |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
4.4.5 | Tech | see catchment investigation schedule |  |  |  | Sample dry flows at key junction manholes for ammonia, chlorine, conductivity, salinity, E.coli (freshwater) or enterococcus (saline or brackish), surfactants, and temperature. All analyses with the exception of indicator bacteria can be performed with field test kits or field instrumentation. | 2.3.4.7 e ii a & 2.3.4.8 c i,ii,iii | 0 | 0 | 877.5817 | 204.3528 | 0 | 0 | 0 | 0 | 0 | 877.5817 | 204.3528 | 0 | 0 | Assumed 10% would have dry weather flows (same assumption as flowing outfalls) and applied per sample costs, with purchase of meter covered under outfall screening and sampling. | WV estimate
4.4.6 | Tech | see wet weather screening schedule |  |  |  | Perform wet weather screening for outfalls with identified System Vulnerability Factors. Sample for same parameters as dry weather flows. | 2.3.4.7 d iv & 2.3.4.7 ii b | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Included in 4.3.3. | WV estimate
4.4.7 | Admin |  | Annual | x | Track progress of Catchment Investigations in each annual report. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See Annual Report cost breakdown | WV estimate
4.5 | [5 empty] | Written IDDE Plan | 2.3.4.7
4.5.1 | Technical | 1 year | One-time |  | Develop written IDDE plan documenting SSOs, outfall/interconnection inventory, statement of program responsibilities, prioritization, outfall screening, catchment investigation procedures, procedures to isolate and verify sources, procedures for removal and confirmation, procedures and schedule for follow-up screening and illicit discharge/SSO prevention procedures. |  | 2.3.4.7 | 16 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 4800 | 16 | 48 | A plan was required under the 2003 permit. Assume low of 16 hours to update an existing plan with catchment prioritization and investigation requirements. Assume 48 hours to develop a plan if one does not exist. | Haverhill: $4,200.
4.5.2 | Admin |  | Intermittent |  | Upon detection of an illicit discharge, identify and notify all responsible parties and require immediate cessation. Should be eliminated within 60 days of identification, or if longer, a schedule developed and report dates of identification and schedules for removal in the permittee's annual reports. |  | 2.3.4.2 a | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 5 | 0 | 4000 | 0 | 40 | Assume investigation performed under PAI 4.3.2A. Assume 8 hours for a brief report for each incident. Assume costs to fix ($2,500 estimated by CWP) are passed along to responsible party. | CWP IDDE Manual: average $2,500 cost per correction, plus additional $500 per investigation
4.5.3 | Tech |  | Intermittent |  | Implement measures to control non-stormwater discharges if they add significant pollution. |  | 2.3.4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Most likely will be zero. Some communities may have a minimal cost. | WV estimate
4.5.4 | Tech |  | One-time |  | Define or describe indicators for tracking program success. Should include measures that demonstrate efforts to locate illicit discharges, the number of SSOs and illicit discharges identified and removed, the percent and area in acres of the catchment area served by the MS4 evaluated using the catchment investigation procedure, and volume of sewage removed. Include in IDDE Plan. |  | 2.3.4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Costs under PAI 4.3.1 | WV estimate
4.6 | [5 empty] | Removal and Confirmation | 2.3.4.7 f
4.6.1 | Admin |  | Annual | x | For each confirmed illicit discharge or SSO, include in the annual report the location of the discharge and its source, a description of the discharge, method and date of discovery, date of elimination, mitigation or enforcement action, and estimate volume removed. |  | 2.3.4.7 f | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | See Annual Report cost breakdown | WV estimate
4.6.2 | Tech | 1 year from removal | Intermittent |  | Within one year of illicit discharge removal, perform confirmatory screening; wet (if System Vulnerability Factors present), dry or both. |  | 2.3.4.7 f | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 56.7647 | 5 | 0 | 8283.8233 | 0 | 80 | Assume 2 people for 4 hours to investigate each incident, and additional 8 hours for a brief report. Cost will vary depending on # of illicit discharges discovered. Assume 0 to 3 per year, consistent with PAI 4.5.2. | WV estimate
4.7 | [5 empty] | Follow-up Screening | 2.3.4.7 g
4.7.1 | Tech | 5 years after catchment investigation | Intermittent |  | Upon completion of catchment investigations and illicit discharge removal and confirmation (if necessary), the catchment outfall or interconnection shall be scheduled for follow-up screening within five years. |  | 2.3.4.7 g | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | This is after the 5-year permit period so no cost carried. In future years, it should be equivalent to dry and wet weather catchment investigations under PAIs 4.3.2, 4.3.3, and 4.3.4. | WV estimate
4.8 |  |  |  | Training
4.8.1 | Admin/Tech |  | Annual |  | Provide annual training to employees involved in IDDE program. |  | 2.3.4.10 | 0 | 0 | 0 | 0 | 20 | 20 | 100 | 500 | 5 | 10500 | 12500 | 100 | 100 |  | WV estimate
4.8.2 | Admin |  | Annual | x | Include type and frequency of training in the annual report. |  | 2.3.4.10 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | See Annual Report cost breakdown | WV estimate
[16 empty] | TOTAL FOR FIVE YEARS (W/O Intermittent Costs) | 48500 | 138000 | 460 | 1330 | High excludes Item 4.4.4 (catchment investigations) since it assumes field mapping of the system, which will cover these costs. Costs do not account for Municipal time to coordinate with consultant.

## Construction Site Control
Task Specific Multipliers
|  |  | Low | High
Consultant Rate |  | 100
Construction Projects per Year |  |  | 1 | 1
| Cost |  | Hours
| Low | High | Low | High
Annual | 0 | 0 | 0 | 0
One-Time | 4200 | 21600 | 32 | 96
Intermittent | 14000 | 24000 | 140 | 240
Total* | 4200 | 21600 | 32 | 96
*Without Intermittent Costs
No. | Type of Action | Time from Effective Date | Frequency | Permit Deliverable | Construction Site Runoff Control Requirement | Reference | One Time Costs |  |  |  | Annual/Ongoing Costs |  |  |  |  | Total Costs/Hours |  |  |  | General Notes | Supporting Documentation
[7 empty] | Hours |  | Fixed Costs |  | Hours per Year |  | Fixed Costs |  | Number of Years | Total Cost Over 5-Year Permit Period |  | Total Hours Over 5-Year Permit Period
[7 empty] | Low | High | Low | High | Low | High | Low | High |  | Low | High | Low | High
1 |  |  |  |  | Develop and implement a construction site runoff program. | 2.3.5 c | [14 empty] | -
1.1 | Admin/ Tech/Legal | Required by 2003 Permit | One-time |  | Develop an ordinance that requires sediment and erosions controls and for other wastes at construction sites. This was required by 2003 MS4 Permit. | 2.3.5 c i | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Required under 2003 Permit and should already be implemented. If not, could be combined with regulatory updated under 1.3.
1.2 | Admin/ Tech | 1 year | One-time |  | Adopt written procedures for inspections and enforcement of the ordinance. Clearly define who is responsible for site inspections and who has authority to implement enforcement procedures. Document in SWMP. | 2.3.5 c ii | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Combined with PAI 1.4.
1.3 | Admin/ Tech/Legal | 1 year | One-time |  | Update ordinance/bylaw to include requirements for site operators to implement BMPs (e.g., reduce disturbed area, protect slopes, etc.) and to control other wastes, if not already included. | 2.3.5 c iii & iv | 32 | 40 | 1000 | 2000 | 0 |  | 0 |  | 0 | 4200 | 6000 | 32 | 40 | Low - Assume 8 hours for meeting with Town including meeting prep time, and 24 hours to review and provide recommendations on regulations. Assume additional legal fees of $1,000. High - Increase meeting time to 16 hours and increase legal fees to $2,000. | WV Estimate. For comparison - Reese: $2,000 for small town, $3,000 for mid-sized town at $50/hr.
1.4 | Admin | 1 year | One-time |  | Develop written procedures for site plan review and inspection and enforcement within 1 year, if not already completed. Include pre-construction review, consideration for protection of water quality impacts, LID components, receipt of information from the public, inspections during and after BMP installation, qualifications necessary to perform the inspections, inspection forms and procedures for tracking the number of site reviews, inspections, and enforcement actions. | 2.3.5 c v | 0 | 56 | 0 | 0 | 0 |  | 0 | 2000 | 5 | 0 | 15600 | 0 | 56 | Required in 2003. Low - Assume 0 hours because it was completed under 2003 permit. High - 16 to outline procedures, 24 hours to develop inspection forms and tracking worksheets, and 16 hours for meetings. Assume town will track site reviews & inspections. Assume additional $2,000 per year for legal to discuss enforcement, etc.). | WV Estimate. For comparison - Reese: $12,000 to develop procedures (140 hours at $50/hr). $10,000 per year for tracking items. Haverhill MA: total cost of $5,600.
1.4a | Tech | 1 year | Intermittent |  | Pre-construction peer reviews | 2.3.5 c v | 0 |  | 0 |  | 24 | 40 | 0 |  | 5 | 12000 | 20000 | 120 | 200 | Pre-construction peer reviews per year. Low - Assume 24 hours per project. High - Assume 40 hours per project, including meetings. | WV Estimate based on performing peer reviews. Includes site visit, peer review, comments, response to comments and meeting(s). For comparison - Reese: $45,000 per year (assumed to employ 1 person for 2 days per week).
1.4b | Tech | 1 year | Intermittent |  | Construction site inspections | 2.3.5 c v | 0 |  | 0 |  | 4 | 8 | 0 |  | 5 | 2000 | 4000 | 20 | 40 | Inspection time will vary from 4-8 hours depending on proximity of site to inspector. Assumes site visit, log completion, photo documentation and preparation of memo by consultant. Assume 1 inspection per project per year. | WV Estimate.
1.5 | Admin |  | Annual | x | Include tracking information as part of each annual report. | 2.3.5 c v | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | See Annual Report cost breakdown | -
[15 empty] | TOTAL FOR FIVE YEARS (w/o intermittent costs) | 4200 | 21600 | 32 | 96

## Post Construction Site Control
Task Specific Multipliers
Consultant Rate |  | 100
Number of permittee-owned facilities for evaluating BMP options |  | 65
| Cost |  | Hours
| Low | High | Low | High
Annual | 0 | 0 | 0 | 0
One-Time | 65200 | 82400 | 622 | 764
Intermittent | 0 | 0 | 0 | 0
Total | 65200 | 82400 | 622 | 764
No. | Type of Action | Time from Effective Date | Frequency | Permit Deliverable | Post Construction Site Runoff Control Requirement | Reference | One Time Costs |  |  |  | Annual/Ongoing Costs |  |  |  | Number of Years | Total Costs/Hours
[7 empty] | Hours |  | Fixed Costs |  | Hours per Year |  | Fixed Costs |  |  | Total Cost Over 5-Year Permit Period |  | Total Hours Over 5-Year Permit Period |  | General Notes | Supporting Documentation
[7 empty] | Low | High | Low | High | Low | High | Low | High |  | Low | High | Low | High
1 |  |  |  |  | Update Ordinance or Bylaw
1.1 | Admin/ Tech/Legal | 2 years | One-time |  | Adopt or amend a local ordinance to control projects that disturb an acre or more. Incorporate design standards included in the permit. | 2.3.6 a ii | 32 | 40 | 1000 | 2000 | 0 |  | 0 |  | 0 | 4200 | 6000 | 32 | 40 | Low - Assume 8 hours for meeting with Town including meeting prep time, and 24 hours to review and provide recommendations on regulations. Assume additional legal fees of $1,000. High - Increase meeting time to 8 hours and legal fees to $2,000. | Reese: $100,000 to work on major policy changes in land use regulations.
1.2 | Admin | 2 years | One-time |  | Develop procedures to ensure O&M, such as dedicated funds or escrow accounts, acceptance of ownership by permittee, development of maintenance contracts between owner & permittee, submission of an annual certification documenting maintenance. | 2.3.6 a iii | 8 | 40 | 1000 | 2000 | 0 |  | 0 |  | 0 | 1800 | 6000 | 8 | 40 | Required in 2003 with less specificity. Low - Assume 8 hours to prepare documentation and $1,000 in legal fees. High - Increase hours to 40 hours and legal fees to $2,000. Note: There will also be an annual fee for the Town to track and follow-up on annual certifications, etc. | WV estimate
1.3 | Admin |  | Annual | x | Annual report shall include measures that the permittee has done to meet these requirements. | 2.3.6 a iii | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | See Annual Report cost breakdown | -
2 |  |  |  |  | Assess Street Design and parking Lot Guidelines
2.1 | Admin/ Tech/Legal | 3 years | One-time |  | Develop report assessing local regulations that affect the creation of impervious cover. Include recommendations and proposed schedules to incorporate into regulations. Involve local planning board and local transportation board. Include in SWMP. | 2.3.6 b | 62 | 116 | 1000 | 2000 | 0 |  | 0 |  | 0 | 7200 | 13600 | 62 | 116 | Low - Assume 40 hours to review regulations and draft report with recommendations, 16 hours to draft regulatory changes, 8 hours for meetings with Town. Include legal fees of $1,000. High - Assume 80 hours to review regulations and draft report with recommendations, 20 hours to draft regulatory changes, 16 hours for meetings with Town. Assume additional legal fees of $2,000. Includes PAI 2.1 and 3.1. (Bumped up the hours a bit because this may be done by someone at a higher rate). | Haverhill MA: total cost of $7,200, combined with 3.1.
2.2 | Admin |  | Annual | x | Annual report shall contain an update on this requirement, including any planned or completed changes. | 2.3.6 b | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | See Annual Report cost breakdown | -
3 |  |  |  |  | LID Regulations and Guidelines
3.1 | Admin/ Tech/Legal | 4 years | One-time |  | Develop report assessing local regulations to determine feasibility of making green roofs, infiltration practices and water harvesting devices allowable. Include recommendations and proposed schedules to incorporate into regulations. | 2.3.6 c | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Costs included under 2.1. | Haverhill MA: total cost of $7,200, combined with 2.1.
3.2 | Admin |  | Annual | x | Annual report shall contain an update on this requirement, including any planned or completed changes. | 2.3.6 c | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | See Annual Report cost breakdown | -
4 |  |  |  |  | Directly Connected Impervious Area
4.1 | Admin |  | Annual | x | Estimate the annual increase or decrease in Impervious Area and Directly Connected Impervious Area using EPA initial estimates of IA and DCIA as baseline. Tabulate results by delineated catchment areas and break out by development, redevelopment, or retrofit projects by permittee; or by private developers and other parties in a voluntary manner or in compliance with the permittee's regulations. Include in annual report. | 2.3.6 d & 2.3.6 d i & ii | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | Per EPA, removed from permit. | -
5 |  |  |  |  | Inventory and Rank Municipal Properties
5.1 | Tech | 4 years | One-time |  | Complete inventory and ranking of Municipal property (including ROWs) suitable for modification or retrofit to reduce runoff/pollutants from MS4. Perform screening level of ranking considering access, geology, depth to water table, proximity to aquifers & subsurface infrastructure, opportunities for public use and education, schedules for planned capital improvements to municipal infrastructure. | 2.3.6 d iii | 520 | 568 | 0 |  | 0 |  | 0 |  | 0 | 52000 | 56800 | 520 | 568 | Low - Assume 8 hours per site to collect information on the site, visit the site in the field, develop preliminary BMP ideas, prepare preliminary maps, prepare rough cost estimates and prioritize sites and document in a report. High - Add 16 hours per selected site to develop conceptual designs of the top 3 sites. Although permit just says to prepare an inventory - really need to evaluate BMP options as well for them to take action on, which is included in this cost. | Haverhill MA: costs of $4,800 for inventory only.
5.2 | Admin | Beginning fifth year | Annual | x | Starting with fifth year annual report, report on status of all such inventoried properties. | 2.3.6 d iv | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | See Annual Report cost breakdown | -
[15 empty] | TOTAL FOR FIVE YEARS | 65200 | 82400 | 622 | 764

## Annual Report
Task Specific Multipliers
Consultant Rate |  | 100
| Cost |  | Hours
| Low | High | Low | High
Annual | 5060 | 10300 | 50.6 | 103
One-Time | 0 | 0 | 0 | 0
Intermittent | 0 | 0 | 0 | 0
Total | 25300 | 51600 | 253 | 516
No. | Type of Action | Time from Effective Date | Frequency | Annual Reporting Requirement |  | Reference | One Time Costs |  |  |  | Annual/Ongoing Costs |  |  |  | Number of Years | Total Cost/Hours |  |  |  | Notes | Supporting Documentation
[7 empty] | Hours |  | Fixed Cost |  | Hours per Year |  | Fixed Costs |  |  | Total Cost Over 5-Year Permit Period |  | Total Hours Over 5-Year Permit Period
[7 empty] | Low | High | Low | High | Low | High | Low | High |  | Low | High | Low | High
4 |  |  |  | Annual Reports |  | 4.3 | [13 empty] | Additional specific items required are covered throughout each minimum measure.
4.1 |  |  | Annually | Submit annual reports including self-assessment review, appropriateness of BMPs, status of impaired waters compliance, items outlined in each of the minimum measures. |  | 4.4 | [8 empty] | 5 | 0 | 0 | 0 | 0 |  | WV estimate
|  |  |  | Meeting with Town | [6 empty] | 4 | 8 |  |  | 5 | 2000 | 4000 | 20 | 40 | Meet with Town and review materials. | WV estimate
|  |  |  | Public Education and Public Participation | [10 empty] | 5 | [5 empty] | WV estimate
|  | all |  |  | Document program in annual report: messages for each audience; method of distribution; measures/methods used to assess effectiveness of message; measures/methods to assess effectiveness. | [5 empty] | 24 | 30 |  |  | 5 | 12000 | 15000 | 120 | 150 | Information should be generated as part of SWMP and public education program. Materials and measures to be attached to annual report. Most hours for measuring the effectiveness of the program. | WV estimate
|  | all |  |  | Report Public Involvement and Public Participation activities in annual report. | [5 empty] | 1 | 2 |  |  | 5 | 500 | 1000 | 5 | 10 |  | WV estimate
IDDE
|  | all |  | 1.2 | Update SSO inventory annually and report in annual report. |  |  |  | 0 | 0 | 0 | 4 |  |  | 5 | 0 | 2000 | 0 | 20 | Minimal cost, if any. Many communities will be zero, and those with SSOs will only be a couple hours. | WV estimate
|  | all |  | 2.2 | Update Outfall Interconnection Survey inventory annually to include data collected from monitoring program. |  |  |  | 0 | 0 | 0 | 4 |  |  | 5 | 0 | 2000 | 0 | 20 | Assume 8 hours to update a database annually. | WV estimate
|  | 2 years |  | 3.6 | Report on progress of Storm System map in annual report. |  |  |  | 0 | 0 | 1 | 2 |  |  | 5 | 500 | 1000 | 5 | 10 | Likely minimal effort. Assume 2 hours per year to include in annual report. | WV estimate
|  | all |  | 4.2.3 | Update assessment & priority ranking annually based on results of screening and new information and include in annual report. Include listing of all catchments and results of ranking, summary of evidence of known or suspected illicit discharges and SSOs by catchment, corrective measures taken or planned, schedule for completing and verifying measures correcting the confirmed illicit discharges and SSOs. |  |  |  | 0 | 0 | 1 | 2 |  |  | 5 | 500 | 1000 | 5 | 10 | Update covered under IDDE. Costs here reflect incorporation into annual report. | WV estimate
[5 empty] | In annual report, include results from any other stormwater or receiving water quality monitoring or studies conducted during the reporting period. | 4.3.c |  |  |  |  | 0 | 8 |  |  | 5 | 0 | 4000 | 0 | 40 | Depends on whether additional data outside the NPDES program is collected and provided to community. | WV estimate
|  | all |  | 4.4.3 | Document and annually report presence or absence of the 12 System Vulnerability Factors for each catchment. |  |  |  | 0 | 0 | 1 | 2 |  |  | 5 | 500 | 1000 | 5 | 10 | Likely minimal effort. Most tracking performed under PAI 4.4.2. Assume 1-2 hours per year to include in annual report. | WV estimate
|  | all |  | 4.4.7 | Track progress of Catchment Investigations in each annual report. |  |  |  | 0 | 0 | 2 | 4 |  |  | 5 | 1000 | 2000 | 10 | 20 | Assume most work performed under PAI 4.4.4 and 4.4.5. Just need to tabulate results into annual report. Assume 2-4 hours to summarize for report. | WV estimate
|  | all |  | 4.6.1 | For each confirmed illicit discharge or SSO, include in the annual report the location of the discharge and its source, a description of the discharge, method and date of discovery, date of elimination, mitigation or enforcement action, and estimate volume removed. |  |  |  | 0 | 0 | 0 | 4 |  |  | 5 | 0 | 2000 | 0 | 20 | Assume field work and most documentation performed under PAI 4.5.2 and 4.6.2. Minimal effort, and possibly zero for communities with no SSOs. Assume 0-4 hours. | WV estimate
|  | all |  | 4.8.2 | Include type and frequency of training in the annual report. |  |  |  | 0 | 0 | 1 | 2 |  |  | 5 | 500 | 1000 | 5 | 10 | Likely minimal effort. Training and most documentation under PAI 4.8.1 Assume 1-2 hours per year to include in annual report. | WV estimate
Construction Site Control
|  | all |  | 1.5 | Include tracking information as part of each annual report. |  |  |  | 0 | 0 | 1 | 2 |  |  | 5 | 500 | 1000 | 5 | 10 | Tracking hours per year. Assume number of site reviews, inspections and enforcement actions tracked under PAI 1.4 with copy of tracking attached to report. | WV estimate
Post Construction Site Control
|  | all |  | 1.3 | Annual report shall include measures that the permittee has done to meet ordinance update requirements. |  |  |  | 0 | 0 | 1 | 2 |  |  | 5 | 500 | 1000 | 5 | 10 | Assume 1-2 hours to report status. | WV estimate
|  | 2 years |  | 2.2 | Annual report shall contain an update on this requirement (Assess Street and Parking Lot Designs), including any planned or completed changes. |  |  |  | 0 | 0 | 1 | 2 |  |  | 4 | 400 | 800 | 4 | 8 | Likely minimal effort. Assume 1-2 hours per year to include in annual report. | WV estimate
|  | 3 years |  | 3.2 | Annual report shall contain an update on this requirement (Assess Local Regulations for LID), including any planned or completed changes. |  |  |  | 0 | 0 | 1 | 2 |  |  | 3 | 300 | 600 | 3 | 6 | Likely minimal effort. Assume 1-2 hours per year to include in annual report. | WV estimate
|  | Beginning fifth year |  | 5.2 | Starting with fifth year annual report, report on status of all Permittee-owned inventoried properties. |  |  |  | 0 | 0 | 1 | 2 |  |  | 1 | 100 | 200 | 1 | 2 | Likely minimal effort. Assume 1-2 hours per year to include in annual report. | WV estimate
Good Housekeeping
|  | all |  |  | In each annual report list the total number of catch basins, number inspected and/or cleaned, and the volume or mass of material removed from each catch basin draining to water quality limited waters and the total volume or mass of material removed from all catch basins. |  |  |  | 0 | 0 | 4 | 8 |  |  | 5 | 2000 | 4000 | 20 | 40 | Review and summarize catch basin cleaning activities. No tracking/compilation costs covered under Good Housekeeping. | WV estimate
|  | all |  |  | Each annual report shall include number of road miles cleaned and volume or mass of material removed. |  |  |  | 0 | 0 | 4 | 8 |  |  | 5 | 2000 | 4000 | 20 | 40 | Review and summarize street sweeping activities. No tracking/compilation costs covered under Good Housekeeping. | WV estimate
|  | all |  |  | Report in the annual report on the status of all O&M activities. |  |  |  | 0 | 0 | 2 | 4 |  |  | 5 | 1000 | 2000 | 10 | 20 | Attach annual inspection logs completed under Good Housekeeping and summarize status of maintenance activities. | WV estimate
|  | 2 years |  |  | Report the findings from the SWPPP Site inspections in the annual report. |  |  |  | 0 | 0 | 2 | 4 |  |  | 5 | 1000 | 2000 | 10 | 20 | Assumes inspections logs will be completed during inspection and attached to the annual report. A few hours to obtain and include information on status of needed improvements identified during inspections. | WV estimate
[15 empty] | TOTAL FOR FIVE YEARS | 25300 | 51600 | 253 | 516

## Miscellaneous
Task Specific Multipliers
Consultant Rate |  | 100
| Cost |  | Hours
| Low | High | Low | High
Annual | 0 | 0 | 0 | 0
One-Time | 0 | 0 | 0 | 0
Intermittent | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0
[7 empty] | One Time Costs |  |  |  | Annual/Ongoing Costs |  |  |  |  | Total Costs/Hours
No. | Type of Action | Time from Effective Date | Frequency | Miscellaneous Requirement |  | Reference | Hours |  | Fixed Costs |  | Hours per Year |  | Fixed Costs |  | Number of Years | Total Cost Over 5-Year Permit Period |  | Total Hours Over 5-Year Permit Period |  | Notes
[7 empty] | Low | High | Low | High | Low | High | Low | High |  | Low | High | Low | High
1 |  |  |  | Discharges to Surface Drinking Water Supplies and Their Tributaries
1.1 | Admin | 1 year | One-time |  | Consider discharges to public surface drinking water supply sources a priority. | 3.0.a | [8 empty] | 1 | 0 | 0 | 0 | 0 | No cost. Incorporated into prioritization matrix.
1.2 | Tech | 1 year | One-time |  | Provide pretreatment and spill control measures to stormwater discharges to public drinking water supply sources or their tributaries to the extent feasible. | 3.0.b | [8 empty] | 1 | 0 | 0 | 0 | 0 | One-time cost, but could be spread over multiple years. To the extent feasible offers some flexibility.
1.3 | Tech |  | Annual |  | Avoid direct discharges to Class A waters to the extent feasible. | 3.0.c | [8 empty] | 5 | 0 | 0 | 0 | 0
[15 empty] | TOTAL FOR FIVE YEARS | 0 | 0 | 0 | 0

## MS4 Stats
| Rural | Suburban | Urban
| 10th percentile | 50th percentile | 90th percentile
Population | 5000 | 15000 | 50000
Assumed number of households | 2000 | 4040 | 20000
Population in Regulated Area | 2000 | 14000 | 45000
Total Area (acres) | 5000 | 10000 | 25000
Total IA (Area) | 500 | 1500 | 3000
# Outfalls | 25 | 773 | 500
# Catch Basins (10 per outfall) | 250 | 7730 | 5000
Consultant Rate per hour | 100 | 100 | 100
Option 1: # Key Junction Manholes (20% of CBs) | 50 | 1546 | 1000
Option 2: # Key Junction Manholes (3 per outfall) | 75 | 2319 | 1500
Range in # Key Junction Manholes | 50 - 75 | 400 - 600 | 1,000 - 1,500
% of structures requiring cleaning (50% full) | 20% | 30% | 40%
# of structures requiring cleaning (50% full) | 50 | 2319 | 2000
% of outfalls flowing under dry weather conditions | 5% | 10% | 15%
# of outfalls flowing under dry weather conditions | 1.25 | 77.3 | 75
# of catchment areas with system Vulnerability Factors for wet weather sampling (25%) | 5 | 193.25 | 150
# of catchment areas with system Vulnerability Factors for wet weather sampling (75%) | 20 | 579.75 | 350
Miles of roadway for sweeping | 10 | 75 | 190
Miles of roadway for sweeping (RM x 2) | 20 | 150 | 380
# of community-owned stormwater BMPs | 5 | 3 | 30
# of permittee-owned facilities for evaluating BMP options and for O & M where there is exposure to stormwater | 5 | 5 | 20

## WQ Analysis Costs
|  | Qty | per sample
bacteria | 50 | 1 | 50 | Alpha Analytical, Westborough, MA - E. Coli Enumeration ($52), Enterococcus ($39); Chemserve, Milford, NH - E. Coli MPN ($27) Enterococcus ($27)
ammonia, package of 30 | 57.5 | 30 | 1.9167 | http://www.benmeadows.com/chemets-ammonia-water-test-kit_s_16806-1/
chlorine and salinity, package of 50 | 45.8 | 50 | 0.916 | http://www.benmeadows.com/lamotte-chloride-salinity-test-kit-pkg-of-50-tests_s_221784/
conductivity and temperature multimeter | 469 |  |  | http://www.benmeadows.com/hanna-waterproof-portable-low-range-multiparameter-meter-_s_57565/
surfactants kit and 20 tests | 78.64 | 20 | 3.932 | http://www.chemetrics.com/Detergents+%28anionic+surfactants%2C+MBAS%29/Visual+Kits/K-9400
surfactants refills 20 tests | 59.82
56.7647

## Cost Scaling Considerations
Cost Options | Potential Application
Municipality Size (e.g., small, medium, large based on population) | NOI, SWMP, Public Education, Regulatory reviews & updates | Could cost for a smaller community and then apply a multiplier for the larger communities.
Miles of Roadway in UA | Street Sweeping
Number of Catch Basins in UA | Catchment investigations, mapping, CB cleaning (with assumptions or just provide a per CB cost)
Number of Outfalls in UA | Dry weather screening, wet weather screening (with assumptions on number with vulnerability factors)
Number of Municipal Facilities | O&M Plans, Retrofit Prioritization
Number of Municipal Facilities with Stormwater Exposure | SWPPPs
Number of Town-owned BMPs | O&M Plan for BMP maintenance
Number of non-TMDL nitrogen impaired waters | Nitrogen Plan
Number of non-TMDL phosphorus impaired waters | Phosphorus Plan